## Project Timeline
Project name |  |  |  | Delivery Date | 2022-09-06 |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  | Apr | [5 empty] | May |  |  |  | June |  |  |  | July |  |  |  |  | Aug |  |  |  |  | Sept |  |  | Oct |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | Aug |  |  |  | Sept |  |  |  |  | Oct |  |  |  | Nov
Category | Event | Evant Date | Action | Start | End | Who | Status | 2022-01-01 | 2022-01-08 | 2022-01-15 | 2022-01-22 | 2022-01-29 | 2022-02-05 | 2022-02-12 | 2022-02-19 | 2022-02-26 | 2022-03-05 | 2022-03-12 | 2022-03-19 | 2022-03-26 | 2022-04-02 | 2022-04-09 | 2022-04-16 | 2022-04-23 | 2022-04-30 | 2022-05-07 | 2022-05-14 | 2022-05-21 | 2022-05-28 | 2022-06-04 | 2022-06-11 | 2022-06-18 | 2022-06-25 | 2022-07-02 | 2022-07-09 | 2022-07-16 | 2022-07-23 | 2022-07-30 | 2022-08-06 | 2022-08-13 | 2022-08-20 | 2022-08-27 | 2022-09-03 | 2022-09-10 | 2022-09-17 | 2022-09-24 | 2022-10-01 | 2022-10-08 | 2022-10-15 | 2022-10-22 | 2022-10-29 | 2022-11-05 | 2022-11-12 | 2022-11-19 | 2022-11-26 | 2022-12-03 | 2022-12-10 | 2022-12-17 | 2022-12-24 | 2022-12-31 | 2023-01-07 | 2023-01-14 | 2023-01-21 | 2023-01-28 | 2023-02-04 | 2023-02-11 | 2023-02-18 | 2023-02-25 | 2023-03-04 | 2023-03-11 | 2023-03-18 | 2023-03-25 | 2023-04-01 | 2023-04-08 | 2023-04-15 | 2023-04-22 | 2023-04-29 | 2023-05-06 | 2023-05-13 | 2023-05-20
Admin | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Forward planning | 2022-05-09 | 2022-05-29 |  | Not Yet Due
Partners | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Presenting Partner Agreement | 2022-05-19 | 2022-06-08 |  | Not Yet Due
Finance | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Funding submissions | 2022-05-29 | 2022-06-18 |  | Not Yet Due
Partners | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Further Partners developed | 2022-06-08 | 2022-06-28 |  | Not Yet Due
Finance | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Budget developed | 2022-06-18 | 2022-07-08 |  | Not Yet Due
Itinerary | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Artist/s Arts workers confirmed & contracted | 2022-06-28 | 2022-07-18 |  | Not Yet Due
Promotions | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Promotional plan | 2022-07-08 | 2022-07-28 |  | Not Yet Due
Promotions | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Flyers designed & printed | 2022-07-28 | 2022-08-17 |  | Not Yet Due
Promotions | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Online promo designed & printed | 2022-07-28 | 2022-08-17 |  | Not Yet Due
Production | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Production Specs | 2022-07-28 | 2022-08-17 |  | Not Yet Due
Show | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Venue needs finalised | 2022-07-28 | 2022-08-17 |  | Not Yet Due
Personnel | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Artsworkers BIOs, bluecards and Pics onfile | 2022-07-28 | 2022-08-17 |  | Not Yet Due
Production | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Stage Plan | 2022-08-07 | 2022-08-27 |  | Not Yet Due
Finance | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Artist / worker invoices received - paid | 2022-08-22 | 2022-09-11 |  | Not Yet Due
Admin | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Final participant numbers | 2022-08-27 | 2022-09-16 |  | Not Yet Due
Admin | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Audience surveys created & undertaken | 2022-09-01 | 2022-09-21 |  | Not Yet Due
Finance | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Final budget | 2022-09-01 | 2022-09-21 |  | Not Yet Due
Schedule | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | WORKSHOP | 2022-09-06 | 2022-09-26 |  | Not Yet Due
Promotions | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Promotions Report Completed | 2022-09-06 | 2022-09-26 |  | Not Yet Due
Partners | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Partner Report Completed | 2022-09-06 | 2022-09-26 |  | Not Yet Due
Admin | BEMAC Presents - Ustad Shahid Parves Khan | 2022-09-06 | Data added to reporting | 2022-09-11 | 2022-10-01 |  | Not Yet Due

## Budget
Expenses | Cost | Responsible | Notes
TOTAL | 0
Income anticipated | Amount | Responsible | Notes
TOTAL | 0

## Artists & Workers
Artist / Worker | Cultural background | Links | Verbal confirmation | Contracted | BIO Received / Final | Promo Pic Received | Postal Address | $ Fee | Schedule / Itinerary sent | Emergency Contacts, Health check, etc confirmed? | ABN | Deposit Invoice Received? | Deposit Paid? | Final invoice received? | Final Invoice paid?

## Schedule
Latest communication notes | To do | Performance / Tour Date | Performance / Activity Time | Activity | Activity Type | Venue | Town | Confirmation | Production Notes | Transport Notes | Contact | Phone | Email | Contact 2 | Phone 2 | Email 2 | Other Notes

## Community Stakeholders
Location | Community Stakeholder | Position Title | Organisation | Phone | Mobile | Email | Street Address | Telephoned? | Invited to launch? | Invited to show?